## Sheet1
Sprint 1 |  |  |  | low med high | low med high
Issue # | User Story / Task Title | Story Points | Description/Associated Tasks | Priority | Risk | Due Date | Responsible
1 | US.1 - As a user, I want to log in so that I can access my account. |  | User Login Functionnality
2 | Create front-end login page | 4 | Developpment of the front-end login page using React: | H | L | 2025-07-02 | Houda
3 | Implement login form with email & password fields | 3 | Create fields for email and passwords | H | L | 2025-07-02 | Houda
4 | Create roles: Admins and members - front-end | 2 | Create fields for role selection | M | M | 2025-07-02 | Houda
5 | Create roles: Admins and members - back-end | 2 | Develop back-end logic for user role selection | M | M | 2025-07-02 | Karan-Yassine
6 | Add error handling for invalid form input | 3 | Implement form validation for login fields | H | L | 2025-07-02 | Nicole
7 | Integrate login with back-end authentication API | 5 |  | H | H | 2025-07-02 | Karan-Yassine
8 | Create dynamic background page | 3 | Design an engaging UI pretty for the eyes | M | L | 2025-07-02 | Nicole
User Sign-up Functionnality
9 | US.2 - As a user, I want to sign up so that I can create my account.
10 | Create front-end user's sign up form | 4 | Developpment of the front-end signup page using React: | H | L | 2025-07-02 | Houda
11 | Implement signup form with name, email, password & role fields | 3 | Create fields for email, passwords and desired roles | H | L | 2025-07-02 | Houda
12 | Add error handling for invalid form input | 3 | Implement form validation for signup fields | H | L | 2025-07-02 | Nicole
13 | Implement a database schema for storing user details | 5 | Design database scheme using SQLite to store user details | H | M | 2025-07-02 | Karan
Admin channel Management
14 | US.3 - As an admin, I want to create channels so that users can have discussions.
15 | Assign users to specific channels - front-end part | 3 | Develop front-end functionnality for assigning users to channel | M | M | 2025-07-02 | Eesha
16 | Assign users to specific channels - backend part | 3 | Develop back-end functionnality for assigning users to channel | M | M | 2025-07-02 | Eesha
17 | Button or scrollable method: create a channel -frontend part | 3 | Develop the UI to create a channel | M | M | 2025-07-02 | Eesha
18 | Button or scrollable method: create a channel -backend part | 3 | Develop the logic to create a channel | M | M | 2025-07-02 | Karan-Yassine
19 | Ensure channels are visible to both admins and users - backend part | 4 | Set the visibility of channels to both admins and users | H | M | 2025-07-02 | Karan-Yassine
20 | Create frontend for admin panel with creating channels functionality in UI | 3 | Develop UI for admin panel with channel management | M | M | 2025-07-02 | Eesha
21 | Create frontend for user page with channels | 3 | Develop the UI for a user to be able to chat | M | M | 2025-07-02 | Eesha
22 | Connect the backend to the login/sign up front end and also the add the navigation functionality | 5 | Integrate the front-end UI/UX with the backend logic so so that when a user or admin logs in it takes them to the right dashboard | H | H | 2025-07-02 | Eesha
23 | Set up a database schema for storing channel details: channel name, type, member list | 5 | Design database scheme to store channels details such as chat logs and media shared | H | H | 2025-07-02 | Karan-Yassine
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
Formulas:
Due Date = [Due Date, row above]